## Example Strategic Roadmap
© 2023 Carlota Sage - Pocket CISO, LLC. Licensed under Creative Commons Attribution 4.0 International
|  | Year 1 |  |  |  | Year 2 |  |  |  | Year 3
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Cybersecurity Program Management
Risk Management | How the organization overall assesses and manages risk, and how cybersecurity supports/fits into organizational risk management | Year 1 Q1: Initial alignment; Year 1 Q2: Continuous business alignment should trigger both at regular time intervals (Monthly/Quarterly/Yearly) and on key activities, such as new product launches, merges & acquisitions, compliance or regulatory changes.
Governance | The policies and functional guidelines governing the organization's business practices, and how cybersecurity supports them. | Year 1 Q1: NIST, CIS, ISO Alignment; Year 1 Q2: Policy, BCP, DRP reviews & updates; Year 1 Q3: Metrics Development and Optimization; Year 2 Q1: Tooling, policy and project management optimization
Privacy | How the organization complies with regulatory requirements and implements best practices for ensuring the privacy of employee and customer information | Year 1 Q1: Research & prioritize C&A requirements; Year 1 Q2: Program Development & Implementation; Year 1 Q3: Ongoing Privacy Review and Updates
Compliance & Audit | What the organization needs to know about global, federal, state and local regulations and industry/voluntarily compliance frameworks | Initial Compliance FW ex: SOC 2, ISO | Initial Compliance FW ex: SOC 2, ISO | Initial Compliance Framework Audit | Compliance Frameworks as required: SOC 2, ISO 27001, FedRAMP, CMMC, HITRUST, etc Internal Audits & Updates |  |  | 2nd Year Audit of Initial Compliance Framework | Compliance reviews & updates | Compliance reviews & updates | Internal Audits & updates | 3rd Year Audit of Initial Compliance FW | Compliance reviews & updates
Vendor Management | How the organization selects and manages vendors, and what they need to understand about risk introduced by vendor practices and technology | Year 1 Q1: Policy & Program Development; Year 1 Q2: Ongoing New & Existing Vendor Management Reviews
Awareness & Training | How the organization keeps employees informed and updated on the cybersecurity information they need to best protect themselves and their customers. | Year 1 Q1: BU awareness & training development; Year 1 Q3: BU awareness & training rolling implementation; Year 2 Q3: Ongoing awareness & training optimization, updates, & delivery
Talent Care and Growth | How the organization ensures its team members stay mentally and emotionally healthy while growing their skillset. A healthy culture is a more secure one. | Year 1 Q1: Determine Hiring Needs & Process; Year 1 Q2: Improve Hiring Process; Year 1 Q3: Individual Certs & Skills Roadmaps; Year 1 Q4: Implement Tabletop Exercises; Year 2 Q1: Continuous hiring process improvement Ongoing security personnel training & development Quarterly or Annual tabletop exercises
Communication Strategy | How an organization communicates its cybersecurity strategy to partners, prospects, customers and the public at large. | Year 1 Q1: Comms Strategy Development, Tool & Business Alignment; Year 1 Q3: Continuous Communications Management, Reviews & Adjustments
Cybersecurity Operations
Identity & Access Management | How employee, developer, partner and customer IDs are created, managed and reviewed. | Year 1 Q1: Initial policy development, tool selection & implementation; Year 1 Q3: Ongoing maintenance, access reviews and process optimization; Year 2 Q2: Yearly review & adjustments; Year 2 Q3: Ongoing maintenance, access reviews and process optimization; Year 3 Q2: Yearly review & adjustments; Year 3 Q3: Ongoing maintenance, access reviews and process optimization
Asset Management | How an organization creates, takes in, discovers, manages and protects hardware, software, data, and internally-developed tooling | Year 1 Q1: Initial asset review, documentation, policy development, tool selection; Year 1 Q2: Ongoing asset management; Year 2 Q1: Yearly asset reconciliation; Year 2 Q2: Ongoing asset management; Year 3 Q1: Yearly asset reconciliation; Year 3 Q2: Ongoing asset management
Physical Security | How an organization protects physical locations and high value personnel. | 3rd Party Physical Security Assessment | Physical security, Disaster Recovery Policy Development | Ongoing maintenance and optimization |  | 3rd Party Assessment | Policy Review & Update | Ongoing maintenance and optimization |  | 3rd Party Assessment | Policy Review & Update | Ongoing maintenance and optimization
Third Party Code & Tool Management | How an organization manages, tracks, updates, and secures code and tools not developed internally | Year 1 Q2: Initial policy development, tool selection & implementation; Year 1 Q4: Ongoing maintenance, access reviews and process optimization; Year 2 Q2: Yearly review & adjustments; Year 2 Q3: Ongoing maintenance, access reviews and process optimization; Year 3 Q2: Yearly review & adjustments; Year 3 Q3: Ongoing maintenance, access reviews and process optimization
Detection | How an organization monitors assets, environments and vendors or 3rd parties for authorized and unauthoried access or potentially malicious behavior. | Year 1 Q1: Initial tool selection & implementation; Year 1 Q3: Ongoing detection optimization; Year 2 Q2: Yearly review & adjustments; Year 2 Q3: Ongoing detection optimization; Year 3 Q2: Yearly review & adjustments; Year 3 Q3: Ongoing detection optimization
Threat Modeling and Intelligence | How an orgnaization takes in information about potential threats to itself, its industry or its customers. | Year 1 Q1: Establish Threat Model & Landscape; Year 1 Q2: ID Threat Feeds/Tool Implementation; Year 1 Q3: Ongoing Threat Management; Year 2 Q3: Yearly Review & Adjustments; Year 2 Q4: Ongoing Threat Management; Year 3 Q3: Yearly Review & Adjustments; Year 3 Q4: Ongoing Threat Management
Vulnerability Management | How an organization identifies and remediates known vulnerabilities in its environments and products, and how it mitigates potential/undiscovered vulnerabilities | Year 1 Q1: Initial policy development, Internal Tooling & Wokflow; Year 1 Q3: Internal Tooling & Wokflow Tuning; Year 2 Q1: Daily operations Internal tooling, policy optimization Continuous documentation updates
Incident Response | How an organization prepares for, responds to, and learns from a perceived or actual cybersecurity threat to its environment | Year 1 Q1: Develop IR Policies, Plans & Playbooks; Year 1 Q2: Identify & Implement IR Tools; Year 1 Q3: IR Management & Optimization; Year 2 Q2: Yearly Review & Table Top Exercises; Year 2 Q3: Ongoing IR Management & Optimization; Year 3 Q2: Yearly Review & Table Top Exercises; Year 3 Q3: Ongoing IR Management & Optimization

## Example Year 1 Strategic Plan
© 2023 Carlota Sage - Pocket CISO, LLC. Licensed under Creative Commons Attribution 4.0 International
Cybersecurity: First Year Strategy
Foundation | New Program Strategic Objectives & Organizational Goals | Key Performance Indicators
Cybersecurity Mission | Cybersecurity Program Management | Success Metrics
Support and enable the business to move as quickly as reasonably possible with security risks and concerns in mind. * Understand the organization's overall strategic initiatives and goals * Provide guidance to decision makers and developers on security requirements | Risk Management: - Develop cadence to meet with every team to align security to their strategic initiatives - Establish thresholds that trigger security engagement/review. | Security Health: Establish baseline, then seek +1 level [in specific domains ¦ across all domains] in the next year.
Governance - Review/develop policies to govern IT/Security going forward. - Review global, federal, regional regulations that apply to organization and ensure policies support these.
Privacy - Ensure privacy laws governing organization are understood and documented within a privacy policy - Create process for receiving and acting on privacy removal requests - Develop pivacy notice for website
Compliance & Audit: - Determine compliance priorities - Establish audit timelines, and tactical roadmaps.
Vendor Management - Develop Vendor Management policy and process for reviewing current and potential vendors
Awareness & Training - Develop and implement security awareness training tailored for each team. Develop general training for onboarding and yearly updates, trickle training for more consistent (weekly/monthly) mindfulness
Talent Care & Growth - Ensure security is embedded into HR onboarding and offboarding processes - Review personnel capabilities and determine skill paths for security/IT teams
Communications Strategy - Establish communication guidelines, processes & procedures for engaging with each team. - Develop external verbiage and comms strategy with legal counsel and PR
Cybersecurity Team's Core Values | Cybersecurity Operations | Vision
Security: Ensure confidentiality, integrity and availability of data and assets. Transparency: Provide clear insights about cybersecurity to employees, executives and Board of Directors. Community: Share lessons learned with your industry and with the security industry at large. | Identity and Access Management - Develop policy and implement tooling | What you want for your team. Examples: "To be a trusted partner within [company] and in the [industry]." "To be known as the most secure provider of [product] in [industry]."
Asset Management - Develop policy and implement tooling
Physical Security - Develop policy and audit schedule
3rd Party Code & Tool Management - Develop standards/guidelines for use of 3rd party components and services in secure application development and infrastructure requirements.
Detection - Develop policy and implement tooling
Threat Modeling & Intelligence - Develop risk and threat models. Determine availble tools in use or to be acquired.
Vulnerability Management - Develop policy and implement tooling
Incident Response - Review current IR procedures and update if needed. - Develop acceptable verbiage with legal counsel for internal and external communications