## Example Year 1 Strategic Plan
Cybersecurity: First Year Strategy
Foundation | New Program Strategic Objectives & Organizational Goals | Key Performance Indicators
Cybersecurity Mission | Cross-functional Relationships | Success Metrics
Support and enable the business to move as quickly as reasonably possible with security risks and concerns in mind. | (1) Business alignment: Meet with every team to understand their strategic initiatives and how security fits in. Have monthly, quarterly and yearly business reviews to ensure ongoing alignment. (2) Awareness & Training: Develop and implement security awareness training tailored for each team. Develop general training for onboarding and yearly updates, trickle training for more consistent (weekly/monthly) mindfulness (3) Compliance & Audit: Determine compliance priorities, audit timelines, and tactical roadmaps. (4) Program & Change Management: Establish communication guidelines, processes & procedures for engaging with each team. Review & update disaster recovery, business continuity plans. Establish thresholds that trigger security engagement/review. | Security Maturity: Establish baseline, then seek +1 level [in specific domains ¦ across all domains] in the next year.
Cybersecurity Team's Core Values | Security Organization | Vision
Security: Ensure confidentiality, integrity and availability of data and assets. Transparency: Provide clear insights about cybersecurity to employees, executives and Board of Directors. Community: Share lessons learned with your industry and with the security industry at large. | (1) Operations: Establish baseline and target security maturity. Establish baseline and target security posture. Review personnel capabilities and determine skill paths. Develop and provide standards and guidelines for secure application development and infrastructure requirements. (2) Emerging Tech/Threats: Develop risk and threat models. Determine availble tools in use or to be acquired. Vulnerability management - detection and remediation. (3) Incident Response: Review current IR procedures and update if needed. Define internal and external communication protocols and guidelines. | What you want for your team. Examples: "To be a trusted partner within [company] and in the [industry]." "To be known as the most secure provider of [product] in [industry]."
Integrate Cybersecurity Requirements with the Business | External Relationships | Implementation
* Understand the organization's overall strategic initiatives and goals * Provide guidance to decision makers and developers on security requirements | (1) Partner Relationships: Ensure that software and platforms used are inventoried and include a way of contacting security. Ensure that contractual obligations for notifying in the event of risk or incident are included in communication protocols. (2) Customer Relationships: Add a security contact to the CRM account file for members and update workflows to support communication protocols. (3) Public Relations: Review Website Privacy Notice and Terms of Use. Ensure there is a path to security for good samaritans reporting security issues. Establish process/relationships needed to get information on the public website quickly. | Formalize the cybersecurity strategy. For a new org, likely: - Level up the security- and privacy-minded personnel across the technical and business teams. - Leverage frameworks to quickly mature security functions.

## Example Strategic Roadmap
LEGEND: Technology Domains
BS | Business Systems | Internal and 3rd-Party systems that support core business functions - things only employees use to support their respective functions
CC | Comms & Collab Platforms | Main website, customer portal, Confluence Wiki, Jira - anything non-service/product a customer, partner or the public may directly access
CS | Cloud Services | The AWS (or other cloud) services and configurations leveraged to host open source applications or internally-developed tools
AD | Application Development | Product applications & services
|  | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Cross-functional Relationships
Business Alignment | What Security needs to know about the Business | Initial alignment | MBR/QBR | MBR/QBR | MBR/QBR | Yearly Alignment | MBR/QBR | MBR/QBR | MBR/QBR | Yearly Alignment | MBR/QBR | MBR/QBR | MBR/QBR | Yearly Alignment | MBR/QBR | MBR/QBR | MBR/QBR
Awareness & Training | What the Business needs to know about Security | Year 1 Q1: BU awareness & training development; Year 1 Q3: BU awareness & training rolling implementation; Year 2 Q3: Ongoing awareness & training optimization, updates, & delivery
Compliance & Audit | What Business and Security need to know about Regulations | Appoint DPA/PM; research & prioritize C&A | PIPEDA? GDPR CS, AD | PIPEDA? GDPR BS, CC | SOC AD | SOC CS | SOC BS, CC | Initial SOC Audit BS, CC, CS, AD | FedRAMP? |  |  | FedRAMP? SOC Audit - Annual | FedRAMP Authorization? | Compliance reviews & updates | Compliance reviews & updates | SOC AUDIT - Annual | Compliance reviews & updates
Program and Change Management | How Security supports and interacts with the Business | Year 1 Q1: Policy, BCP, DRP reviews & updates; Year 1 Q3: Tooling & workflow updates; Year 2 Q1: Tooling, policy and project management optimization
Cybersecurity Operations
Program & People Development | How Security functions | Year 1 Q1: CIS, NIST implementation BS, CC; Year 1 Q2: CIS, NIST implementation BS, CC, CS, AD; Year 1 Q3: CIS, NIST implementation BS, CC, CS, AD; Year 1 Q4: CIS, NIST implementation BS, CC, CS, AD; Year 2 Q1: CIS, NIST implementation CS, AD; Year 2 Q2: NIST Framework Tuning; Year 2 Q3: NIST Framework Tuning; Year 2 Q4: Ongoing resource optimization & documentation
|  |  | Metrics Baseline: BS, CC | Metrics Baseline: BS, CC, CS, AD | Metrics Baseline: BS, CC, CS, AD | Metrics Baseline: BS, CC, CS, AD | Metrics Baseline CS, AD | Metrics Tuning |  |  |  | Metrics Optimization
|  | Establish/Doc Internal Tooling & Wokflow | Internal Tooling & Wokflow Tuning | Daily operations Quarterly tabletop exercises Internal tooling, policy optimization Continuous documentation updates Ongoing security personnel training & development
|  | Individual Certs & Skills Roadmaps | Implement Tabletop Exercises
Asset Management | What Security needs to secure | Year 1 Q1: Initial asset review & documentation; Year 1 Q2: Ongoing asset management; Year 2 Q1: Yearly asset reconciliation; Year 2 Q2: Ongoing asset management; Year 3 Q1: Yearly asset reconciliation; Year 3 Q2: Ongoing asset management; Year 4 Q1: Yearly asset reconciliation; Year 4 Q2: Ongoing asset management
Detection | How Security monitors assets and environments | Year 1 Q1: Initial tool selection & implementation; Year 1 Q3: Ongoing detection optimization; Year 2 Q2: Yearly review & adjustments; Year 2 Q3: Ongoing detection optimization; Year 3 Q2: Yearly review & adjustments; Year 3 Q3: Ongoing detection optimization; Year 4 Q2: Yearly review & adjustments; Year 4 Q3: Ongoing detection optimization
Emerging Threats & Vulnerability Mgmt | What Security needs to know about external risk | Year 1 Q1: Establish Threat Model & Landscape; Year 1 Q2: ID Threat Feeds/Tool Implementation; Year 1 Q3: Ongoing Threat Management; Year 2 Q3: Yearly Review & Adjustments; Year 2 Q4: Ongoing Threat Management; Year 3 Q3: Yearly Review & Adjustments; Year 3 Q4: Ongoing Threat Management; Year 4 Q3: Yearly Review & Adjustments; Year 4 Q4: Ongoing…
Incident Response | How Security responds to immediate threats | Year 1 Q1: Develop IR Policies, Plans & Playbooks; Year 1 Q2: Identify & Implement IR Tools. Tabletops; Year 1 Q3: Ongoing IR Management & Optimization; Year 2 Q4: Yearly Review & Major Adjustments; Year 3 Q1: Ongoing IR Management & Optimization; Year 3 Q4: Yearly Review & Major Adjustments; Year 4 Q1: Ongoing IR Management & Optimization; Year 4 Q4: Yearly Review & Major Adjustments
Communication Strategy | How Security communicates what's happening | Year 1 Q1: Comms Strategy Development, Tool & Business Alignment; Year 1 Q3: Continuous Communications Management, Reviews & Adjustments
External Relationships
Partner Relationships | How Security interacts with external Partners | 3rd Party Platform Review | 3rd Party Platform Review | Partner Yearly Review | Partner QBR | Partner QBR | Partner QBR | Partner Yearly Review | Partner QBR | Partner QBR | Partner QBR | Partner Yearly Review | Partner QBR | Partner QBR | Partner QBR | Partner Yearly Review | Partner QBR
Customer Relationships | How Security interacts with external Customers | Doc CC Platform Requirements | CC Platform Implementation & Testing | CC Platform Switchover | Monthly/ Quarterly Insights | Monthly/ Quarterly/ Yearend Insights | Monthly/ Quarterly Insights | Monthly/ Quarterly Insights | Monthly/ Quarterly Insights | Monthly/ Quarterly/ Yearend Insights | Monthly/ Quarterly Insights | Monthly/ Quarterly Insights | Monthly/ Quarterly Insights | Monthly/ Quarterly/ Yearend Insights | Monthly/ Quarterly Insights | Monthly/ Quarterly Insights | Monthly/ Quarterly Insights
Public Relations | How Security presents itself to the public at large | Develop PR & Crisis Playbooks | Quarterly Review | Quarterly Review | Quarterly Review | Yearly Review | Quarterly Review | Quarterly Review | Quarterly Review | Yearly Review | Quarterly Review | Quarterly Review | Quarterly Review | Yearly Review | Quarterly Review | Quarterly Review | Quarterly Review
Note on C10: Carlota Sage: Security leadership needs understand how the mission & goals of each BU support the overall organization
Note on C11: Carlota Sage: Awareness & Training should be tailored to each specific business unit. Your finance department should be especially aware of phishing and have a direct contact in the security org, for example, but doesn't need to study for the CISSP…
Note on C12: Carlota Sage: Compliance shouldn't stand alone; tie it to organizational goals and initiatives.
Note on C13: Carlota Sage: Ensure your cybersecurity team is included in the business' RACI matrices, invited into project discussions early, and that cybersecurity is a key stakeholder in business continuity and disaster recovery plans.
Note on C15: Carlota Sage: Determine operational and organizational metrics - the metrics you need to function daily vs. the metrics that demonstrate security's role in achieving organizational goals.
Note on C21: Carlota Sage: Ensure the tools (technical and non-technical) in use are keeping your cybersecurity team aware and up-to-date with the changing threat landscape for your business, your industry, and informaton security in general.
Note on C22: Carlota Sage: How your team identifies and deals with weirdness in your environment, including practice runs, documentation and, when appropriate, engaging law enforcement or the security community at large.
Note on C23: Carlota Sage: How your team documents and communicates what's happening in your environment
Note on C25: Carlota Sage: Security should understand and have insight into 3rd Party Relationships, whether they're product integrations or vendor platforms.
Note on C26: Carlota Sage: Security should understand the organization's customer base, their needs and how the organization's products/services serve them. Security should be visible/accessible outside of a major incident.
Note on C27: Carlota Sage: How the cybersecurity team addresses security concerns from the general public (social media, good summaritan reporting, news items); participation in bug bounties; visibility within the organization's industry or the security industry.